## Status Document
RRD | [5 empty] | QAT Lead: | Danny Petsis, Anil Reddy, Imran Khan
Reporting Date: | [5 empty] | QAT Testers: | James Scoght, Sue Benoit
RAG |  |  | Status | Highlights & Comments |  |  | Last Week’s Overall Status |  |  |  | Issue Summary
This Week’s Overall Status |  |  | G |  |  |  | Last Week | G | # Weeks at Status | 1
Project Updates
File # |  | RRD File Name |  |  | Scotiabank Internal File Name | Chase Internal File Name |  |  |  |  | Output required | # of records | Header | Trailer | Type of records | Date Sent | Expected Date for Output | Date Received | Status | Comments
Sample | File Type | R338022501E.TST |  |  | [BNS File Name] | ECRV.DEIFCD.C3.CHIPREIS.TO.GND.G1703V00 |  |  |  |  | PDF, Full Package - White Plastics, Card Carrier, Inserts, Activation Sticker | 9 |  |  | Reissue | 2015-02-25 |  | 2015-02-25 | In Progress | Regression File
QAT Shakedown | Statement Fiile | TBD |  |  | TBD | TBD |  |  |  |  | PDF | TBD |  |  | TBD | TBD | TBD |  |  | • Currently on hold within BNS so the sample reprint file has not been sent to RRD
QAT Shakedown | Correspondence File | TBD |  |  | TBD | TBD |  |  |  |  | PDF | TBD |  |  | TBD | 2016-07-05 | 2016-07-08 |  |  | • Conditioned yesterday(4th July), Cathy picked up the file from the Chase landing zone but the JO landing zone doesn’t seem to have the file for the July 5. Natalie will research and confirmed a correspondence file was sent to JO at 1:32 am. The plan is to send to RRD later today. (Update – file was sent RRD later in the day)
QAT 1.0 | Statement Fiile | TBD |  |  | TBD | TBD |  |  |  |  | PDF | TBD |  |  | TBD | 2016-07-15 | 2016-07-21 |  |  | • RRD Statements start July 15 (Maleha owns)
QAT 1.0 | Correspondence File | TBD |  |  |  | TBD |  |  |  |  | PDF | TBD |  |  | TBD | 2016-07-11 | 2016-07-15 |  |  | see comments above from row 15
QAT 2.0 | Statement Fiile | TBD |  |  | TBD | TBD |  |  |  |  | Normalized File, AFP, Physical Output | TBD |  |  | TBD | 2016-07-25 | 2016-07-29 |  |  | see comments above from row 14 and 16
QAT 2.0 | Correspondence File | TBD |  |  | TBD | TBD |  |  |  |  | Normalized File, AFP, Physical Output | TBD |  |  | TBD | 2016-07-25 | 2016-07-29 |  |  | see comments above from row 15
QAT 3.0 | Statement Fiile | TBD |  |  | TBD | TBD |  |  |  |  | Normalized File, AFP, Physical Output | TBD |  |  | TBD | 2016-08-08 | 2016-08-12 |  |  | see comments above from row 14 and 16
QAT 3.0 | Correspondence File | TBD |  |  | TBD | TBD |  |  |  |  | Normalized File, AFP, Physical Output | TBD |  |  | TBD | 2016-08-08 | 2016-08-12 |  |  | see comments above from row 15
Update# |  | Date |  |  |  | Comments